## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to submit a bug report for analysis. | Must | None | Rohit | Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want to upload screenshots or log files. | Should | US-01 | Rohit | Completed
Sprint 1 | Sprint 1 | US-03 | As a user, I want the system to retrieve similar bugs using FAISS. | Must | US-01 | Rohit | Completed
Sprint 1 | Sprint 1 | US-04 | As a user, I want bug category and priority prediction. | Must | US-03 | Rohit | Completed
Sprint 1 | Sprint 1 | US-05 | As a user, I want offline AI-generated fix suggestions. | Must | US-04 | Rohit | Completed
Sprint 1 | Sprint 1 | US-06 | As a user, I want to view the analysis results in a dashboard. | Should | US-05 | Rohit | Completed
Sprint 2 | Sprint 2 | US-07 | As a user, I want the system to automatically triage bugs by severity, priority, and component. | Must | US-06 | Rohit | Completed
Sprint 2 | Sprint 2 | US-08 | As a user, I want the system to analyze uploaded logs and extract exception details automatically. | Must | US-07 | Rohit | Completed
Sprint 2 | Sprint 2 | US-09 | As a user, I want all AI agents to work together and generate a complete bug analysis report. | Must | US-08 | Rohit | Completed
Sprint 2 | Sprint 2 | US-10 | As a user, I want the frontend to communicate with the backend and display the analysis results. | Should | US-09 | Rohit | Completed
Sprint 4 | Sprint 4 | US-07 | As a project stakeholder, I want defect pattern analytics so that recurring bug themes, affected components, severity trends, and root-cause patterns can be identified. | Must | US-06 | Rohit | Completed
Sprint 4 | Sprint 4 | US-08 | As a developer, I want verified resolved bugs to be added to the knowledge base so that future bug analysis can use confirmed historical defect information. | Must | US-03 | Rohit | Completed
Sprint 4 | Sprint 4 | US-09 | As a developer, I want end-to-end testing across different bug types and stack trace formats so that the complete analysis pipeline can be validated. | Must | US-07 | Rohit | Completed
Sprint 4 | Sprint 4 | US-10 | As a project stakeholder, I want technical documentation and a final project demonstration so that the complete system can be presented and maintained. | Should | US-09 | Rohit | Completed
450 line
there are so many why are you telling me to push the code you dont have the sense
Pasted code(1).py
Python
Pasted code(2).py
Python
is this is need for the project in the milestone 2
this is not filpkart 8.0
in the end there is a button called analyzer another bug or something now it is not there
Copy of Unit_Test_Plan_v0.1.xls
Spreadsheet
Copy of Defect_Tracker Template_v0.1.xls
Spreadsheet
Copy of Agile_Template_v0.1.xls
Spreadsheet
Yesterday 8:17 PM
Copy of Defect_Tracker Template_v0.1(1).xls
Spreadsheet
please give what to update in the file
Copy of Unit_Test_Plan_v0.1(1).xls
Spreadsheet
please give what to update in the file
Stopped thinking
Your Unit Test Plan currently has 6 test cases. Since you completed Milestone 2, you should add new test cases instead of changing the existing ones.
Add these rows after Sl. No. 6:
Sl. No | Test Case Name | Test Procedure | Condition to be Tested | Expected Result | Actual Result
7 | Triage Agent | Submit a bug report | Valid bug description | Severity, priority, component and confidence are displayed correctly | Passed
8 | Log Analysis Agent | Submit a bug report containing a stack trace | Valid exception log | Exception type, failure point, line number and error message are extracted correctly | Passed
9 | JSON Report Generation | Analyze a bug report | Valid bug report | JSON analysis report is generated and stored successfully | Passed
10 | Frontend–Backend Integration | Submit a bug from the web interface | Valid user request | Data is processed successfully and analysis results are displayed on the result page | Passed
11 | Multi-Agent Workflow | Submit a bug report | Valid bug report | Triage Agent, Log Analysis Agent, Similar Bug Retrieval and AI Fix Advisor execute successfully | Passed
12 | Result Dashboard | Analyze a bug | Completed analysis | Dashboard displays all analysis sections correctly | Passed
Final Unit Test Plan
Existing Test Cases (1–6): Keep unchanged
Add New Test Cases (7–12): For Milestone 2
This will make your Unit Test Plan reflect the new functionality you implemented in Milestone 2.
Copy of Agile_Template_v0.1(1).xls
Spreadsheet
Stopped thinking
I checked your Agile_Template. It currently contains only Sprint 1 information. For Milestone 2, you should append Sprint 2 entries instead of modifying Sprint 1.
1. Product Backlog
Add these rows after US-06:
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
S
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 128 | 83 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
| Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Estimate (Hours) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
US-01 | T-01 | Project Setup using Flask | 2026-07-01 | 2026-07-01 | Rohit | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-02 | Collect Mozilla Bug Dataset | 2026-07-01 | 2026-07-02 | Rohit | Data Collection | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-03 | Preprocess Dataset | 2026-07-02 | 2026-07-02 | Rohit | Data Cleaning | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-04 | Generate Embeddings using Sentence Transformers | 2026-07-03 | 2026-07-03 | Rohit | AI Development | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-05 | Build FAISS Vector Database | 2026-07-03 | 2026-07-04 | Rohit | AI Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-06 | Similar Bug Retrieval | 2026-07-04 | 2026-07-04 | Rohit | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-07 | Offline AI Recommendation Engine | 2026-07-05 | 2026-07-05 | Rohit | AI Development | Completed | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-08 | Result Dashboard Design | 2026-07-05 | 2026-07-06 | Rohit | UI Design | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-09 | Testing and Debugging | 2026-07-06 | 2026-07-07 | Rohit | Testing | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-10 | Documentation | 2026-07-07 | 2026-07-07 | Rohit | Documentation | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-11 | Develop Triage Agent | 2026-07-13 | 2026-07-14 | Rohit | AI Development | Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-12 | Integrate Triage Agent with Flask | 2026-07-14 | 2026-07-14 | Rohit | Development | Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-13 | Develop Log Analysis Agent | 2026-07-15 | 2026-07-16 | Rohit | AI Development | Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-14 | Parse Stack Traces and Error Messages | 2026-07-16 | 2026-07-16 | Rohit | Development | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-15 | Implement Multi-Agent Workflow | 2026-07-17 | 2026-07-18 | Rohit | Integration | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-16 | Generate JSON Analysis Report | 2026-07-18 | 2026-07-18 | Rohit | Development | Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-17 | Connect Frontend with Backend | 2026-07-18 | 2026-07-19 | Rohit | Integration | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-18 | System Testing and Debugging | 2026-07-19 | 2026-07-19 | Rohit | Testing | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-19 | Update Documentation and README | 2026-07-19 | 2026-07-19 | Rohit | Documentation | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-20 | Integrate Ollama LLM for Triage and Log Analysis | 2026-07-19 | 2026-07-20 | Rohit | AI Development | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-11 | Develop Defect Pattern Analytics Module | 2026-08-11 | 2026-08-12 | Rohit | Development | Completed | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-12 | Implement Severity and Component Trend Analytics | 2026-08-12 | 2026-08-12 | Rohit | Development | Completed | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-13 | Implement Root Cause and Recurring Defect Analytics | 2026-08-13 | 2026-08-13 | Rohit | Development | Completed | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-14 | Integrate Defect Analytics Dashboard | 2026-08-13 | 2026-08-14 | Rohit | Integration | Completed | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-15 | Implement Verified Bug Knowledge Base Storage | 2026-08-14 | 2026-08-14 | Rohit | Development | Completed | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-16 | Implement Knowledge Base Growth Mechanism | 2026-08-15 | 2026-08-15 | Rohit | Development | Completed | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-17 | Rebuild FAISS Knowledge Base Index | 2026-08-15 | 2026-08-15 | Rohit | AI Development | Completed | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-18 | Prepare Five Distinct Bug Test Cases | 2026-08-16 | 2026-08-16 | Rohit | Testing | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-19 | Perform End-to-End Testing | 2026-08-16 | 2026-08-17 | Rohit | Testing | Completed | 6 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-20 | Validate Duplicate Detection and Fix Recommendations | 2026-08-17 | 2026-08-17 | Rohit | Testing | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-21 | Prepare Technical Documentation | 2026-08-18 | 2026-08-18 | Rohit | Documentation | Completed | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-22 | Update README and Agile Documentation | 2026-08-19 | 2026-08-19 | Rohit | Documentation | Completed | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-23 | Prepare Final Demonstration Materials | 2026-08-20 | 2026-08-20 | Rohit | Documentation | Completed | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Dataset preparation | Collected Mozilla Bug Dataset
Sprint 1 | Day 2 | Data cleaning | Preprocessed dataset successfully
Sprint 1 | Day 3 | FAISS integration | Built FAISS vector database
Sprint 1 | Day 4 | UI alignment issues | Improved dashboard layout
Sprint 1 | Day 5 | Offline AI implementation | Developed rule-based recommendation engine
Sprint 1 | Day 6 | GitHub push issue | Fixed Git configuration and pushed project
Sprint 1 | Day 7 | Documentation preparation | Completed README and project documentation
Sprint 2 | Day 1 | Triage logic refinement | Updated severity and priority rules
Sprint 2 | Day 2 | Stack trace parsing issue | Improved regex patterns
Sprint 2 | Day 3 | Frontend-backend integration | Fixed Flask routing and templates
Sprint 2 | Day 4 | JSON generation issue | Corrected report generation
Sprint 2 | Day 5 | Dashboard display issue | Updated result page layout
Sprint 2 | Day 6 | Testing and debugging | Validated all AI modules
Sprint 2 | Day 7 | Documentation | Updated README and project documents
Sprint 4 | Day 1 | Defect analytics data organization | Implemented defect pattern analytics for recurring themes and affected components
Sprint 4 | Day 2 | Analytics categorization issues | Added severity, component, exception, and root-cause analysis
Sprint 4 | Day 3 | Knowledge base update workflow | Implemented verified resolved-bug storage
Sprint 4 | Day 4 | FAISS index synchronization | Rebuilt FAISS index after adding verified bugs
Sprint 4 | Day 5 | Duplicate detection validation | Tested duplicate detection using multiple bug scenarios
Sprint 4 | Day 6 | End-to-end testing across different defects | Tested five distinct bugs through the complete multi-agent pipeline
Sprint 4 | Day 7 | Final documentation and submission preparation | Updated README, Agile documentation, GitHub repository, and final demo materials

## Retrospection
SL# | Sprint# | Sprint Start Date | Sprint End Date | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 2026-07-01 | 2026-07-07 | Rohit | Using semantic search | Using API keys | Improving UI | Replaced Gemini API with Offline AI
2 | Sprint 1 | 2026-07-01 | 2026-07-07 | Rohit | Better testing | Hardcoded values | Code optimization | Improved recommendation engine
3 | Sprint 1 | 2026-07-01 | 2026-07-07 | Rohit | Documentation | Unused code | Debugging | Updated README
4 | Sprint 1 | 2026-07-01 | 2026-07-07 | Rohit | Better UI | Old dashboard | Responsive design | Redesigned Result Page
5 | Sprint 1 | 2026-07-01 | 2026-07-07 | Rohit | Improve AI suggestions | API dependency | Offline processing | Offline AI completed
6 | Sprint 2 | 2026-07-13 | 2026-07-19 | Rohit | Multi-Agent integration | Manual log inspection | Code optimization | Integrated Triage and Log Analysis Agents
7 | Sprint 2 | 2026-07-13 | 2026-07-19 | Rohit | Automated testing | Repetitive debugging | Documentation | Completed Milestone 2 deliverables
8 | Sprint 2 | 2026-07-13 | 2026-07-19 | Rohit | Prompt Engineering | Hardcoded AI responses | AI-based development | Improved LLM prompt for complete JSON output
9 | Sprint 2 | 2026-07-13 | 2026-07-19 | Rohit | Multi-error log analysis | Manual exception tracing | Testing | Implemented support for multiple log issue
10 | Sprint 4 | 2026-08-11 | 2026-08-20 | Rohit | Systematic end-to-end validation | Testing only individual modules | Complete pipeline testing | Tested five distinct bugs through the complete multi-agent pipeline
11 | Sprint 4 | 2026-08-11 | 2026-08-20 | Rohit | Defect pattern analysis | Manual analysis of recurring defects | Data-driven analytics | Implemented Defect Pattern Analytics Dashboard
12 | Sprint 4 | 2026-08-11 | 2026-08-20 | Rohit | Verify resolved bugs before knowledge-base updates | Adding unverified defects | Maintaining verified historical knowledge | Implemented Knowledge Base Growth Mechanism
13 | Sprint 4 | 2026-08-11 | 2026-08-20 | Rohit | Validate FAISS updates after knowledge-base growth | Manual index handling | Automated knowledge-base indexing | Rebuilt FAISS index after verified bug addition
14 | Sprint 4 | 2026-08-11 | 2026-08-20 | Rohit | Validate duplicate detection with varied defects | Assuming similarity means duplication | Similarity-based validation | Tested duplicate detection across multiple bug scenarios
15 | Sprint 4 | 2026-08-11 | 2026-08-20 | Rohit | Maintain documentation during development | Delaying documentation | Maintaining project documentation | Updated README and Agile documentation