## Defects
No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | Rohit | 2026-07-02 | Pandas import error during execution | Sprint 1 | Vyshnavi | Logical | Reinstalled pandas and recreated virtual environment | 2026-07-02 | Closed | Fixed successfully
2 | Rohit | 2026-07-03 | FAISS similarity search not returning results | Sprint 1 | Vyshnavi | Logical | Rebuilt FAISS vector database | 2026-07-03 | Closed | Working correctly
3 | Rohit | 2026-07-04 | Result page UI alignment issue | Sprint 1 | Vyshnavi | User Interface | Updated HTML and CSS layout | 2026-07-04 | Closed | Dashboard improved
4 | Rohit | 2026-07-05 | GitHub push failed because of venv | Sprint 1 | Vyshnavi | Maintainability | Added .gitignore and removed venv from tracking | 2026-07-05 | Closed | Repository updated
5 | Rohit | 2026-07-06 | AI recommendation output formatting issue | Sprint 1 | Vyshnavi | Standards | Improved recommendation formatting | 2026-07-06 | Closed | Better readability
6 | Rohit | 2026-07-18 | Log Analysis Agent failed to extract exception details from some stack traces | Sprint 2 | Vyshnavi | Logical | Improved log parsing logic and regex patterns | 2026-07-18 | Closed | Fixed successfully
7 | Rohit | 2026-07-18 | Triage Agent returned incorrect priority for certain bug reports | Sprint 2 | Vyshnavi | Logical | Updated classification rules for severity and priority | 2026-07-18 | Closed | Predictions improved
8 | Rohit | 2026-07-19 | Result page did not display AI analysis correctly | Sprint 2 | Vyshnavi | User Interface | Updated Jinja template and result page layout | 2026-07-19 | Closed | Output displayed correctly
9 | Rohit | 2026-07-21 | Log Analysis Agent returned invalid JSON output | Sprint 2 | Vyshnavi | Logical | Added JSON parsing fallback using regex | 2026-07-21 | Closed | Fixed successfully
10 | Rohit | 2026-07-22 | Result page could not display multiple log issues | Sprint 2 | Vyshnavi | User Interface | Updated Jinja template to iterate through the issues array | 2026-07-22 | Closed | Multiple issues displayed correctly
11 | Rohit | 2026-07-22 | f-string prompt caused ValueError while generating AI prompt | Sprint 2 | Vyshnavi | Standards | Escaped JSON braces ({{ }}) inside the prompt | 2026-07-22 | Closed | Prompt working correctly
12 | Rohit | 2026-07-22 | Duplicate code in app.py caused syntax error | Sprint 2 | Vyshnavi | Maintainability | Removed duplicate code and corrected indentation | 2026-07-22 | Closed | Application executed successfully
13 | Rohit | 2026-07-22 | Root Cause and Suggested Fix fields were empty | Sprint 2 | Vyshnavi | Logical | Improved Ollama prompt with complete JSON example | 2026-07-22 | Closed | AI generates complete an
14 | Rohit | 2026-08-11 | Defect analytics did not initially display recurring defect patterns correctly | Sprint 4 | Vyshnavi | Logical | Implemented defect pattern analytics for recurring themes and affected components | 2026-08-12 | Closed | Analytics displayed correctly
15 | Rohit | 2026-08-12 | Severity and component trend analysis required refinement | Sprint 4 | Vyshnavi | Logical | Added severity and component aggregation and validation | 2026-08-12 | Closed | Trends validated successfully
16 | Rohit | 2026-08-13 | Root cause and exception patterns were not available in analytics | Sprint 4 | Vyshnavi | Logical | Added root cause and exception pattern analysis | 2026-08-13 | Closed | Pattern analysis working correctly
17 | Rohit | 2026-08-14 | Verified resolved bug was not automatically reflected in the historical knowledge base | Sprint 4 | Vyshnavi | Logical | Implemented verified bug storage and knowledge base growth workflow | 2026-08-15 | Closed | Resolved bugs added successfully
18 | Rohit | 2026-08-15 | FAISS index required updating after knowledge base growth | Sprint 4 | Vyshnavi | Logical | Implemented FAISS index rebuild after verified bug addition | 2026-08-15 | Closed | FAISS index updated successfully
19 | Rohit | 2026-08-16 | Duplicate detection required validation across different bug scenarios | Sprint 4 | Vyshnavi | Logical | Tested semantic similarity and duplicate detection using multiple bug reports | 2026-08-17 | Closed | Duplicate detection validated
20 | Rohit | 2026-08-16 | End-to-end pipeline required validation using multiple defect types | Sprint 4 | Vyshnavi | Testing | Tested five distinct bugs through triage, log analysis, root cause, duplicate detection and remediation | 2026-08-17 | Closed | Five bug scenarios successfully tested
21 | Rohit | 2026-08-18 | Knowledge base growth workflow required final verification | Sprint 4 | Vyshnavi | Testing | Verified resolved bugs and confirmed knowledge base and FAISS index updates | 2026-08-18 | Closed | Knowledge base growth verified
22 | Rohit | 2026-08-19 | Technical documentation required final update | Sprint 4 | Vyshnavi | Documentation | Updated README, Agile documentation and project documentation | 2026-08-20 | Closed | Documentation completed
23 | Rohit | 2026-08-20 | Final project demonstration required complete pipeline validation | Sprint 4 | Vyshnavi | Testing | Prepared final demonstration using complete multi-agent analysis workflow | 2026-08-20 | Closed | Final demonstration ready

## Sheet2
Category | Count
Logical | 13
User Interface | 3
Maintainability | 2
Standards | 2
Others | 4
Total | 24